TAS2O Capstone Showcase / Demo Day Plan

Technology and the Skilled Trades, Grade 10, Open | AI-Enhanced Implementation

| Field | Information |
| --- | --- |
| School Name | Webtree Academy |
| BSID | 883796 |
| Course | TAS2O - Technology and the Skilled Trades, Grade 10, Open, 1.0 Credit |
| Teacher | Carlos Chen |
| Principal / Academic Lead | Henry Michels |
| Showcase Date | To be scheduled |
| Location | Webtree Academy lab / hall / online as approved |
| Version / Revision Date | To be scheduled |

Purpose of this document This plan organizes the TAS2O final capstone showcase, prototype demonstrations, student presentations, assessment evidence collection, audience feedback, media consent controls, and post-event filing. It is designed to support a safe, well-documented final evaluation and to provide inspection-ready evidence that student work was evaluated against course expectations.

# Table of Contents

1. Showcase Purpose and Learning Evidence

2. Event Roles and Responsibilities

3. Pre-Event Preparation Timeline

4. Demo Day Schedule Template

5. Room Layout and Safety Controls

6. Student Presentation Requirements

7. Prototype Demonstration Rules

8. Assessment and Judging Workflow

9. Audience Feedback Form

10. Media, Photo, Video, and Privacy Controls

11. AI Use and Academic Integrity Checks

12. Emergency / No-Go Decision Protocol

13. Post-Event Evidence Filing Checklist

14. Templates and Sign-Off Forms

# 1. Showcase Purpose and Learning Evidence

The capstone showcase is the culminating public or semi-public demonstration of student learning in TAS2O. Students present a prototype, product, service concept, digital model, or automation solution developed through the engineering design process. The event should align with the school's assessment, privacy, and student-record procedures so that evidence can be filed consistently after the event and stored in the course evidence binder.

| Evidence Area | What Students Demonstrate | Possible Evidence |
| --- | --- | --- |
| Engineering design process | Problem definition, criteria, constraints, iteration, testing, refinement | Design portfolio, sketches, CAD files, test data, prototype photos |
| Safe practical work | Appropriate tool use, PPE, prototype testing boundaries | Safety sign-off, teacher observation notes, demo-day checklist |
| Technological development | Understanding of materials, systems, automation, CAD, or physical computing | Prototype, wiring diagram, CAD model, technical explanation |
| AI literacy | Responsible use of AI as assistant, not replacement | AI Use Log, verification notes, student reflection |
| Communication | Clear explanation of problem, solution, evidence, limitations, and next steps | Oral presentation, poster, slides, audience Q&A |
| Career and impact connection | Link to skilled trades, technology careers, sustainability, accessibility, or community needs | Career reflection, impact analysis, final portfolio section |

# 2. Event Roles and Responsibilities

| Role | Primary Responsibilities | Required Before Event |
| --- | --- | --- |
| TAS2O Teacher | Confirm readiness of student projects, assess presentations, enforce safety rules, collect evidence | Final project list, rubric copies, safety checks, media consent roster |
| Principal / Academic Lead | Approve final showcase plan, support safety and supervision, review assessment process if needed | Sign-off on event plan and room readiness |
| Lab / Safety Supervisor | Inspect demo stations, confirm tools are locked away unless authorized, support emergency readiness | Lab setup checklist, first aid/emergency information |
| Students | Set up prototype, present work, follow safety rules, answer questions, submit portfolio | Final portfolio, AI Use Log, presentation materials |
| Guest Reviewers / Judges | Provide non-binding feedback unless officially part of assessment plan | Reviewer briefing sheet and feedback form |
| Office / Admin | Manage visitor sign-in, consent restrictions, room access, emergency contact information | Visitor list, consent restrictions, emergency contacts |

# 3. Pre-Event Preparation Timeline

| Timeframe | Teacher / School Tasks | Student Tasks | Evidence to File |
| --- | --- | --- | --- |
| 4 weeks before | Confirm capstone requirements, demo format, safety restrictions, presentation format | Finalize problem statement and prototype plan | Approved proposal and safety plan |
| 3 weeks before | Review prototype risks and required materials | Build / iterate prototype; collect testing data | Progress photos and teacher conference notes |
| 2 weeks before | Check media consent status; create event schedule | Draft poster/slides; update AI Use Log | Draft portfolio checkpoint |
| 1 week before | Run practice demos; identify no-go prototypes; prepare room layout | Rehearse 3-5 minute presentation; finalize portfolio | Practice feedback and revised plan |
| 1 day before | Inspect room, PPE, tables, power, signage, first aid, device charging | Bring prototype, backup files, poster/slides | Room setup checklist |
| Event day | Run setup, presentation, assessment, feedback, media controls | Present, demo safely, answer questions | Rubrics, photos if consented, feedback forms |
| After event | Finalize grades, file evidence, debrief safety/assessment issues | Submit final reflection if not already completed | Final evaluation sign-off and evidence binder |

# 4. Demo Day Schedule Template

| Time | Activity | Responsible Person | Notes |
| --- | --- | --- | --- |
| 8:30-9:00 | Teacher setup and station safety inspection | Teacher / Safety Lead | No students operate prototypes until inspection is complete. |
| 9:00-9:15 | Student arrival and station setup | Students / Teacher | Power cords, sharp objects, hot tools, and liquids checked. |
| 9:15-9:25 | Safety briefing and event rules | Teacher | Review no-go rules and emergency exits. |
| 9:25-10:45 | Round 1 presentations / station visits | Students / Reviewers | 3-5 minutes per student or small group. |
| 10:45-11:00 | Break and reset | Teacher / Students | No unsupervised prototype operation. |
| 11:00-12:15 | Round 2 presentations / Q&A | Students / Reviewers | Teacher collects assessment evidence. |
| 12:15-12:30 | Audience feedback collection | Admin / Teacher | Collect forms before dismissal. |
| 12:30-1:00 | Cleanup and equipment check-in | Students / Teacher | Complete sign-out/in and room reset. |
| After event | Teacher assessment finalization | Teacher | File rubrics and final evidence. |

# 5. Room Layout and Safety Controls

☐ Display room map with entrances, exits, first aid location, and teacher station.

☐ Place projects requiring power near approved outlets; do not allow extension cords across walking paths unless taped and approved.

☐ Create a no-student-access tool storage zone; all tools not required for demonstration remain locked away.

☐ Use only low-voltage demonstrations unless a teacher has explicitly approved and supervised the setup.

☐ Keep soldering, cutting, drilling, heat tools, and powered fabrication activities closed during showcase unless specifically authorized in writing.

☐ Provide a quiet station or alternative presentation format for students requiring accommodations.

☐ Clearly mark any project that may be touched and any project that is display-only.

☐ Set up one teacher-controlled charging / battery / power check station if needed.

Default showcase rule The showcase is for demonstration and explanation, not active fabrication. Cutting, soldering, drilling, hot glue work, and tool-based modification should not occur during the event unless explicitly authorized and supervised by the TAS2O teacher.

# 6. Student Presentation Requirements

Each student or group should prepare a short, structured presentation. The teacher may adjust timing for class size and accommodations.

| Presentation Component | Required Content | Suggested Time |
| --- | --- | --- |
| Problem and user | Who is the solution for? What problem is being addressed? | 30-45 sec |
| Design criteria and constraints | What must the solution do? What limits affected the design? | 30-45 sec |
| Prototype / model explanation | How does it work? What materials or systems are used? | 60-90 sec |
| Testing and quality control | What data or observations show whether it worked? | 45-60 sec |
| use of approved AI tools disclosure | How was use of approved AI toolsd? How was AI output verified or revised? | 30-45 sec |
| Impact and career connection | How does this connect to technology, skilled trades, accessibility, sustainability, or careers? | 30-45 sec |
| Next iteration | What would be improved next? | 20-30 sec |

# 7. Prototype Demonstration Rules

| Prototype Type | Allowed During Showcase | Not Allowed Unless Specifically Authorized |
| --- | --- | --- |
| CAD / digital model | Screen display, rotation, screenshots, design explanation | Unsupervised student login to unrelated accounts or public AI tools |
| 3D printed / physical prototype | Handling if safe, static display, fit/function demonstration | Cutting, melting, drilling, sanding, active printing in crowded area |
| micro:bit / Arduino / low-voltage electronics | Teacher-approved low-voltage demo, LEDs, sensors, buzzers at safe volume | Exposed unsafe wiring, damaged batteries, liquids near electronics |
| Assistive / accessibility design | Non-invasive demonstration with student-created scenario | Testing on people without consent or unsafe physical contact |
| Structural model | Load test only if teacher-approved and safe zone is created | Uncontrolled dropping, throwing, collapse risk near audience |
| documentation | Display verified user manual, checklist, poster, or reflection | Displaying private prompts, personal information, or unverified claims as facts |

# 8. Assessment and Judging Workflow

The teacher remains responsible for final assessment. Guest reviewer feedback can support communication, reflection, and student learning, but should not replace teacher professional judgment unless the school has approved a formal co-assessment process.

| Assessment Evidence | Collected By | When | Filed Where |
| --- | --- | --- | --- |
| Final capstone rubric | Teacher | During or immediately after presentation | Assessment binder / student file |
| Portfolio checklist | Teacher / Student | Before event or event day | Student portfolio folder |
| Prototype photo/video if consented | Teacher / Approved staff | During event | Media folder with consent controls |
| Audience feedback form | Guests / peers | During event | Feedback folder; not primary grade evidence |
| AI Use Log verification | Teacher | Before final grade submission | Academic integrity / AI evidence file |
| Safety sign-off | Teacher / Safety Lead | Before demonstrations begin | Safety evidence binder |

Judging guidance Avoid ranking students publicly unless the school has a clear policy and inclusive rationale. A safer format is “feedback categories” such as Most Thoughtful Iteration, Strongest User Research, Strong Technical Explanation, Strong Sustainability Connection, and Strongest Safety Documentation.

# 9. Audience Feedback Form

Use the following form for peers, families, or guest reviewers. This is formative feedback unless explicitly included in the approved assessment plan.

| Student / Group | Project Title | Reviewer Name | Reviewer Role |
| --- | --- | --- | --- |
| TBD | TBD | TBD | Peer / Parent / Guest / Staff |

| Criteria | Feedback Prompt | Rating / Notes |
| --- | --- | --- |
| Problem clarity | The student clearly explained the user need or problem. | 1 2 3 4 ¦ Notes: |
| Prototype function | The prototype or model showed a reasonable solution. | 1 2 3 4 ¦ Notes: |
| Testing evidence | The student used data, observations, or feedback to improve the design. | 1 2 3 4 ¦ Notes: |
| Communication | The student explained technical ideas clearly and professionally. | 1 2 3 4 ¦ Notes: |
| AI responsibility | The student explained how AI was used and verified. | 1 2 3 4 ¦ Notes: |
| Next steps | One helpful suggestion for improvement: | Notes: |

# 10. Media, Photo, Video, and Privacy Controls

☐ Review the Photo / Video / Portfolio Consent Form before the event.

☐ Prepare a consent roster showing which students may be photographed, filmed, named, or displayed publicly.

☐ Use color-coded table cards or teacher-only notes to identify consent restrictions discreetly.

☐ Do not post student images, names, or work publicly unless optional public media consent is clearly granted.

☐ Keep assessment-required evidence separate from marketing or promotional materials.

☐ Do not capture AI prompts or screenshots that include personal information, private accounts, or identifiable data.

☐ Allow students who decline public media use to participate fully without academic penalty.

| Student Name | Photo Internal Evidence | Video Internal Evidence | Public Website/Social Media | Name Display | Restrictions |
| --- | --- | --- | --- | --- | --- |
| TBD | Yes / No | Yes / No | Yes / No | Full / First / None | TBD |
| TBD | Yes / No | Yes / No | Yes / No | Full / First / None | TBD |
| TBD | Yes / No | Yes / No | Yes / No | Full / First / None | TBD |

# 11. AI Use and Academic Integrity Checks

Because the TAS2O implementation intentionally includes AI-enhanced learning, the showcase should include a clear but age-appropriate AI disclosure component.

| Checkpoint | Teacher Question | Evidence |
| --- | --- | --- |
| use of approved AI tools disclosure | Can the student explain what AI helped with and what they personally created? | AI Use Log and oral explanation |
| Verification | Did the student verify safety, technical, or career information? | Source notes, teacher checks, revised output |
| Ownership | Can the student demonstrate understanding of code, CAD decisions, or design reasoning? | Q&A and prototype explanation |
| Privacy | Did the student avoid entering personal, confidential, or sensitive information into AI tools? | Student declaration and teacher observation |
| No fabrication | Are testing data, sources, and prototype claims real and supported? | Portfolio, data table, observation evidence |

# 12. Emergency / No-Go Decision Protocol

Teacher authority The TAS2O teacher, principal, or safety lead may stop any demonstration at any time if there is a safety, supervision, privacy, or academic integrity concern.

| Concern | Immediate Action | Follow-Up |
| --- | --- | --- |
| Unsafe wiring, heat, sharp edges, unstable structure | Stop demonstration; unplug or isolate project; move audience back | Record issue and assess static explanation only |
| Student missing required safety approval | Do not allow active demonstration | Permit poster/CAD explanation if safe |
| Media consent uncertainty | Do not photograph or film student/project until verified | Check consent form and update roster |
| AI misuse concern | Ask student to explain process; defer final judgment if needed | Review AI Use Log and portfolio before grading |
| Emergency / injury / near miss | Follow school emergency procedure and incident reporting process | Complete incident / near-miss form and notify admin |

# 13. Post-Event Evidence Filing Checklist

☐ Final capstone rubrics completed and signed/dated by teacher.

☐ Student portfolios collected or confirmed in LMS / Drive folder.

☐ AI Use Logs checked and filed with assessment evidence.

☐ Prototype photos/videos filed only according to consent permissions.

☐ Audience feedback forms collected and separated from official marks unless approved assessment evidence.

☐ Safety sign-off and any incident/near-miss reports filed.

☐ Attendance for event day and make-up presentations recorded.

☐ Final grade calculation updated in markbook.

☐ Report card comments supported by documented evidence.

☐ Teacher reflection completed for next course revision.

# 14. Templates and Sign-Off Forms

## 14.1 Student Demo Station Card

| Field | Student Completes |
| --- | --- |
| Student / Group Name | TBD |
| Project Title | TBD |
| Problem Addressed | Student presentations, prototype demos, and portfolio review are completed under supervision. |
| Prototype Type | CAD / physical / electronics / service / mixed |
| Can audience touch it? | Yes / No / Ask first |
| Power required? | No / Battery / Outlet - teacher approved |
| AI was used for | Brainstorming / research / debugging / writing support / other |

## 14.2 Teacher Final Showcase Sign-Off

| Item | Yes / No / Notes |
| --- | --- |
| Room setup completed and checked |  |
| Emergency readiness confirmed |  |
| Consent roster reviewed |  |
| No-go projects identified and managed |  |
| Rubrics and assessment tools prepared |  |
| Student portfolios and AI logs collected or scheduled |  |
| Evidence filed after event |  |

## 14.3 Approval and Revision Record

| Name / Role | Signature | Date | Notes |
| --- | --- | --- | --- |
| TAS2O Teacher |  |  |  |
| Principal / Academic Lead |  |  |  |
| Safety Lead / Lab Supervisor, if applicable |  |  |  |